## Sheet1
Bug ID | Description | Who Found It | Cause | Fix | Status
1 | Command help and ? Unable to display commands | ricky | The switch statement for it was invalid | Used appropriate switch statement | Fixed
2 | Game menu caused infinite loop | ricky | Loop code for menu was out of place | Restructured the loops for the separate game menus | Fixed
3 | Game could still start with name field empty | ricky | No validation for name input | Name input validation to check for empty input | Fixed
4 | Current location would not print when first starting game | ricky | Currentlocation was a separate method | gameInstructions updated | Fixed
5 | Solve command has no input for empty locations | ricky | No else statement to handle | Else statement to handle empty locations added | Fixed
6 | Item.getname unable to invoke | ricky | return value of location item getter was null | added item to location | fixed
7 | command use after cryo core activation displays non unique message | ricky | wrong if statement order | unique eventtriggered message added first in if statement | fixed
8 | look command has no message for empty location | ricky | empty space location has no long description | added various long descriptions with random selection | fixed
9 | Monolith/Strix puzzles can be spammed | ricky | no event triggering for puzzles | After a correct answer, trigger event and reformat checking | fixed
10 | quit command accepts characters other than y or n | ricky | confirmation doesn't enforce y or n | Wrap the confirmation in a loop that continues prompting until y or n | fixed
11 | currentLocation method not printing hostility after location constructor refactor | ricky | locationclass wasn’t set up properly | Refactor Location class to include hostility parameter | fixed
12 | mastermind combat triggered even after correct puzzle | ricky | incorrect puzzle logic in combat logic | puzzle logic removed from combat logic | fixed
13 | combat infinite loop | ricky | combat loop incorrectly structured | refactored combat loop | fixed
14 | can still trade with enemies after defeating | ricky | no enemy death check for trade logic | added enemy death check to fight command | fixed
15 | player can still get cryo core even after solving mastermind puzzle | ricky | combat logic doesn’t check for cryocore in inventory | added cryocore check in combatsystem | fixed